## QuickKart_Business_Requirements
Requirement_ID | Business_Requirement | Stakeholder | Priority | Verification_Method | Implementation_Status | Approval_Status
BR-001 | Monitor daily sales file submissions from all 50 stores | Operations Manager | High | Check expected vs received store files | Implemented | Draft
BR-002 | Identify missing store files before report approval | Operations Manager | High | Test by removing one store file | Implemented | Draft
BR-003 | Detect invalid and duplicate sales transactions | Data Analyst | High | Run data quality validation checks | Implemented | Draft
BR-004 | Block daily reporting when required files or data are invalid | Operations Manager | High | Test BLOCKED status on failure | Implemented | Draft
BR-005 | Generate approved daily sales output after successful validation | Data Analyst | High | Verify approved CSV and PASS status | Implemented | Draft
BR-006 | Monitor sales revenue, gross profit, units and transactions | Sales Manager | High | Check Power BI KPI calculations | Implemented | Draft
BR-007 | Analyze sales by month, location, city and product category | Sales Manager | High | Test Power BI charts and slicers | Implemented | Draft
BR-008 | Review product profitability and sales performance | Finance Manager | Medium | Check Product Analysis dashboard | Implemented | Draft
BR-009 | Maintain execution logs and exception reports for daily processing | Operations Manager | High | Check JSON status and failure logs | Implemented | Draft
BR-010 | Refresh published dashboards automatically with approved reporting data | Management | Medium | Verify approved Neon data reconciliation and Power BI scheduled refresh history; fresh-batch order monitored separately | Implemented - Cloud scheduled refresh tested | Draft

## Stakeholder_Clarification_Log
Clarification_ID | Requirement_ID | Stakeholder | Clarification_Question | Proposed_Business_Rule | Status
CL-001 | BR-001 | Operations Manager | What is the daily file submission deadline? | All 50 stores should submit files by 8:15 AM | Pending Confirmation
CL-002 | BR-002 | Operations Manager | What happens if a store file is missing? | Block daily report approval until missing files are resolved | Pending Confirmation
CL-003 | BR-003 | Data Analyst | How should duplicate Sale IDs be handled? | Flag duplicate transactions for investigation | Pending Confirmation
CL-004 | BR-003 | Finance Manager | Should zero or negative units be allowed for refunds? | Current simulated sales process requires positive units; refund handling needs clarification | Pending Confirmation
CL-005 | BR-004 | Operations Manager | Can the report be approved when invalid records exist? | Block approved output until validation passes | Pending Confirmation
CL-006 | BR-005 | Data Analyst | Which file format should approved reporting use? | Generate approved sales data in CSV format | Pending Confirmation
CL-007 | BR-006 | Finance Manager | How should gross profit be calculated? | Gross Profit = SUM(Units × (Product_Price - Product_Cost)); excludes operating expenses | Pending Confirmation
CL-008 | BR-007 | Sales Manager | Which reporting dimensions are required? | Month, Store Location, City and Product Category | Pending Confirmation
CL-009 | BR-009 | Operations Manager | How should failed automation runs be tracked? | Generate execution logs and exception reports | Pending Confirmation
CL-010 | BR-010 | Management | When should the Power BI dashboard refresh? | Target Power BI refresh: 10:00 AM IST after approved Neon load; verify production schedule restored after tests | Pending Confirmation

## Requirement_Traceability_Matrix
Requirement_ID | Requirement_Summary | Implementation_Reference | Technical_Evidence | Implementation_Status | Formal_UAT_Signoff | FRD_ID | BRD_Reference | FRD_Reference | Mapping_Status
BR-001 | Monitor daily store file submissions | ctl_Expected_Store_Files; ctl_Received_Store_Files; ctl_Daily_File_Status | 50 expected and 50 received files | Implemented | Pending external sign-off (technical UAT recorded) | FR-001 | Section 6 - BR-001 | Section 3 - FR-001 | Mapped
BR-002 | Detect missing store files | qc_Missing_Branch_Files; Python daily pipeline | Store 4 missing file detected | Implemented | Pending external sign-off (technical UAT recorded) | FR-002 | Section 6 - BR-002 | Section 3 - FR-002 | Mapped
BR-003 | Validate sales transactions | qc_Daily_Sales_Quality; qc_Daily_Sales_Exceptions | Invalid Units test and exception detection | Implemented | Pending external sign-off (technical UAT recorded) | FR-003 | Section 6 - BR-003 | Section 3 - FR-003 | Mapped
BR-004 | Block incomplete or invalid reports | gate_Daily_Sales; out_Daily_Approved; Python daily pipeline | BLOCKED status with 49 received files | Implemented | Pending external sign-off (technical UAT recorded) | FR-004 | Section 6 - BR-004 | Section 3 - FR-004 | Mapped
BR-005 | Export approved daily sales | 03_Approved_Output; run_daily_quality_pipeline.py | PASS status and 1500 approved rows | Implemented | Pending external sign-off (technical UAT recorded) | FR-005 | Section 6 - BR-005 | Section 3 - FR-005 | Mapped
BR-006 | Monitor sales KPIs | Executive Overview; Measure_table | Sales; Gross Profit; Units; Transactions cards | Implemented | Pending external sign-off (technical UAT recorded) | FR-006 | Section 6 - BR-006 | Section 3 - FR-006 | Mapped
BR-007 | Analyze sales by month and dimensions | Sales Analysis Power BI page | Monthly charts; location and category slicers | Implemented | Pending external sign-off (technical UAT recorded) | FR-007 | Section 6 - BR-007 | Section 3 - FR-007 | Mapped
BR-008 | Analyze product profitability | Product Analysis Power BI page | Category performance; product ranking; profit margin | Implemented | Pending external sign-off (technical UAT recorded) | FR-008 | Section 6 - BR-008 | Section 3 - FR-008 | Mapped
BR-009 | Track pipeline logs and exceptions | 04_Automation_Logs; Python daily pipeline | JSON PASS/BLOCKED logs and exception CSV | Implemented | Pending external sign-off (technical UAT recorded) | FR-009 | Section 6 - BR-009 | Section 3 - FR-009 | Mapped
BR-010 | Automatically refresh published dashboards | GitHub Actions quality gate → Neon daily.approved_sales → Power BI Service cloud semantic model | 30-Oct-2026: 7,500 rows / 9,852 units matched in Neon and Power BI; GitHub scheduled #7 success; Power BI scheduled + later on-demand refresh completed; new-batch unattended sequencing unverified | Implemented - Scheduled cloud runs verified | Pending external sign-off (technical UAT recorded) | FR-010 | Section 6 - BR-010 | Section 3 - FR-010 | Mapped

## Business_Rules_Summary
Rule_ID | Requirement_ID | Business_Rule | Expected_System_Behavior | Priority | Confirmation_Status
RULE-001 | BR-001 | All 50 stores must submit daily sales files | Compare 50 expected files with received files | High | Pending Stakeholder Confirmation
RULE-002 | BR-002 | If any required store file is missing, daily approval must be blocked | Return BLOCKED status and identify missing file | High | Pending Stakeholder Confirmation
RULE-003 | BR-003 | Sale ID must be unique within the reporting batch | Detect and flag duplicate Sale IDs | High | Pending Stakeholder Confirmation
RULE-004 | BR-003 | Units must be positive for the current sales-only scenario | Flag zero or negative Units as invalid | High | Pending Stakeholder Confirmation
RULE-005 | BR-003 | Store ID and Product ID must exist in master data | Flag unknown Store IDs and Product IDs | High | Pending Stakeholder Confirmation
RULE-006 | BR-004 | Invalid transactions must not enter the approved daily output | Block approval if any transaction fails validation | High | Pending Stakeholder Confirmation
RULE-007 | BR-005 | Approved daily sales must be exported as CSV | Generate approved CSV only when checks pass | High | Pending Stakeholder Confirmation
RULE-008 | BR-006 | Gross Profit equals Sales Amount minus Cost Amount | Calculate Gross Profit consistently in reporting | High | Pending Stakeholder Confirmation
RULE-009 | BR-009 | Every pipeline execution must record its result | Maintain PASS or BLOCKED status and execution logs | High | Pending Stakeholder Confirmation
RULE-010 | BR-010 | Dashboard refresh must use approved data only | Refresh reporting after validated output is available | Medium | Pending Stakeholder Confirmation

## Agile_User_Stories
Story_ID | Requirement_ID | Role | User_Story | Priority | Story_Status
US-001 | BR-001 | Operations Manager | As an Operations Manager, I want to monitor daily file submissions from 50 stores, so that I can track reporting completeness. | High | Implemented in simulation (approval pending)
US-002 | BR-002 | Operations Manager | As an Operations Manager, I want to identify missing store files, so that incomplete reports are not approved. | High | Implemented in simulation (approval pending)
US-003 | BR-003 | Data Analyst | As a Data Analyst, I want to detect invalid and duplicate transactions, so that reporting data remains accurate. | High | Implemented in simulation (approval pending)
US-004 | BR-004 | Operations Manager | As an Operations Manager, I want to block invalid daily reporting batches, so that incorrect data is not approved. | High | Implemented in simulation (approval pending)
US-005 | BR-005 | Data Analyst | As a Data Analyst, I want to generate approved daily sales CSV files, so that validated data is available for reporting. | High | Implemented in simulation (approval pending)
US-006 | BR-006 | Sales Manager | As a Sales Manager, I want to monitor sales, profit, units and transactions, so that I can evaluate business performance. | High | Implemented in simulation (approval pending)
US-007 | BR-007 | Sales Manager | As a Sales Manager, I want to analyze sales by month, city, location and category, so that I can identify performance trends. | High | Implemented in simulation (approval pending)
US-008 | BR-008 | Finance Manager | As a Finance Manager, I want to analyze product profitability, so that I can identify high and low performing products. | Medium | Implemented in simulation (approval pending)
US-009 | BR-009 | Operations Manager | As an Operations Manager, I want to review execution logs and exceptions, so that I can investigate reporting failures. | High | Implemented in simulation (approval pending)
US-010 | BR-010 | Management | As a Management User, I want dashboards to refresh automatically using approved data, so that I can view updated information. | Medium | Implemented - scheduled cloud runs; E2E sequencing pending

## Acceptance_Criteria
AC_ID | Story_ID | Given | When | Then | Priority | Status
AC-001 | US-001 | 50 store files are expected for a reporting date | All 50 correct store files are available | System shows 50 expected, 50 received and zero missing | High | Technically tested - signoff pending
AC-002 | US-001 | Daily folders contain files for multiple dates | The reporting pipeline processes the selected reporting date | Only the required date's POS files are included | High | Technically tested - signoff pending
AC-003 | US-002 | 50 store files are expected | Store 4 CSV file is missing | System identifies Store 4 filename and returns BLOCKED | High | Technically tested - signoff pending
AC-004 | US-003 | A daily sales batch contains transactions | Two transactions contain the same Sale_ID | System flags duplicate Sale IDs | High | Technically tested - signoff pending
AC-005 | US-003 | Daily sales transactions are loaded | A transaction has Units less than or equal to zero | System flags Invalid Units | High | Technically tested - signoff pending
AC-006 | US-003 | Product and Store master data are available | A transaction contains an unknown Product_ID or Store_ID | System identifies the invalid master data reference | High | Technically tested - signoff pending
AC-007 | US-003 | A reporting date is defined | A transaction belongs to a different date | System flags Wrong Reporting Date | High | Technically tested - signoff pending
AC-008 | US-004 | Daily file and transaction validation is active | At least one required check fails | System blocks approval and provides a failure reason | High | Technically tested - signoff pending
AC-009 | US-005 | All 50 files and all transactions pass validation | The daily quality pipeline completes | System generates an approved CSV containing 1500 rows for the simulated test batch | High | Technically tested - signoff pending
AC-010 | US-006 | Validated historical sales data is available | A user opens the Executive Overview dashboard | System displays sales, gross profit, units and transactions KPIs | High | Technically tested - signoff pending
AC-011 | US-007 | Sales Analysis dashboard is available | A user selects a month, city, location or category | Relevant charts and KPIs update according to the selected filters | High | Technically tested - signoff pending
AC-012 | US-008 | Product Analysis dashboard is available | A user reviews product categories and products | System displays revenue, profit, margin and product performance | Medium | Technically tested - signoff pending
AC-013 | US-009 | The daily pipeline completes successfully | Execution logs are generated | Logs contain PASS status, reporting date and approved row count | High | Technically tested - signoff pending
AC-014 | US-009 | A required store file is missing | The daily pipeline fails validation | Logs contain BLOCKED status and the missing filename | High | Technically tested - signoff pending
AC-015 | US-010 | An approved reporting dataset becomes available | The automatic dashboard refresh process runs | Only approved data is used and refresh outcome is recorded | Medium | Technical refresh evidenced; unattended same-batch ordering not yet independently proven; sign-off pending

## UAT_Test_Cases
Test_Case_ID | AC_ID | Test_Scenario | Test_Steps | Expected_Result | Test_Status | Actual_Result | Evidence
TC-001 | AC-001 | All Store Files Received | Run daily pipeline with 50 valid POS files | 50 received and 0 missing | PASS | 50 expected; 50 received; 0 missing; 1,500 approved transactions; PASS on 2026-10-19. | 2026-10-19_status.json
TC-002 | AC-002 | Correct Reporting Date | Add sales folders for two dates and refresh reporting query | Only required date files are processed | PASS | Power Query counted 51 available files: 50 selected-date files and 1 other-date file. | TC-002_Date_Isolation.png
TC-003 | AC-003 | Missing Store File | Temporarily remove Store 4 CSV and run pipeline | Status BLOCKED and missing filename logged | PASS | Original failure run: 49/50 files; S004 missing; BLOCKED; approved rows = 0. | TC-003_Missing_Store_BLOCKED.log (source: 2026-10-19_141718_952381_run.log)
TC-004 | AC-004 | Duplicate Sale ID | Add a duplicate Sale_ID and run validation | Duplicate Sale ID flagged | PASS | Original failure run: duplicate Sale_ID in S003 CSV line 3; BLOCKED; approved rows = 0. | TC-004_Duplicate_Sale_ID_BLOCKED.log (source: 2026-10-19_011148_208947_run.log)
TC-005 | AC-005 | Invalid Units | In an isolated synthetic batch set Units to -3; run the original Python quality validation. | Invalid Units issue detected | PASS | Isolated Python validation with Units = -3 detected INVALID_TRANSACTION; BLOCKED; 0 approved. | TC-005_Invalid_Units_validation_exceptions.csv + isolated BLOCKED LOG/JSON
TC-006 | AC-006 | Unknown Product or Store ID | In isolated synthetic batches test unknown Product_ID and Store_ID; correct inputs and rerun. | Unknown master reference detected | PASS | Isolated Python tests identified unknown Product_ID and Store_ID (9999); BLOCKED; recovery PASS with 1,500 rows. | TC-006_Unknown_Product_Store_ID_Evidence (01_BLOCKED / 02_Recovery_PASS)
TC-007 | AC-007 | Wrong Reporting Date | In an isolated synthetic batch change a transaction date to another day; correct and rerun. | Wrong Reporting Date detected | PASS | Isolated Python test flagged 2026-10-20 transaction within 2026-10-19 batch; BLOCKED; recovery PASS, 1,500 rows. | TC-007_Wrong_Reporting_Date_Evidence (01_BLOCKED / 02_Recovery_PASS)
TC-008 | AC-008 | Report Approval Blocking | Validate an invalid isolated batch; verify approval blocked; correct and rerun. | Approved output blocked and failure logged | PASS | Reused isolated TC-007 test: invalid batch BLOCKED, approved rows = 0; after fix PASS, 1,500 approved. | TC-008_Report_Approval_Blocking_Evidence (01_BLOCKED / 02_Recovery_PASS)
TC-009 | AC-009 | Successful Approved CSV | Run isolated validation with all valid simulated store files and review exported approved CSV. | Approved CSV contains 1500 transactions | PASS | Isolated PASS output CSV: 1,500 transactions, 1,500 unique Sale_IDs, 50 stores, no missing values. | TC-009_Approved_Sales_2026-10-19_Isolated_Test.csv
TC-010 | AC-010 | Executive Dashboard KPIs | Open Executive Overview and verify KPI measures | Sales profit units and transactions displayed correctly | PASS | Executive Overview displays historical sales $14.44M, gross profit $4.01M, transactions ~829K, margin 27.79%. | 01_Executive_Overview.png
TC-011 | AC-011 | Dashboard Filter Interaction | Compare Sales Analysis baseline against Store Location = Downtown filter (BEFORE / AFTER). | Relevant visuals and KPIs respond correctly | PASS | User confirms BEFORE / AFTER Sales Analysis filter screenshots and visual response; AFTER image not reviewed here. | TC-011_Sales_All_Filters_Before_REAL.png; TC-011_Store_Location_Downtown_After.png
TC-012 | AC-012 | Product Performance Analysis | Inspect product revenue / profit / margin and compare baseline to selected Toys category. | Revenue profit margin and product performance visible | PASS | Product Analysis baseline verified; user confirms category-selection interaction screenshot; selected view not reviewed here. | TC-012_Product_Analysis_REAL.png; TC-012_Product_Toys_Selected.png
TC-013 | AC-013 | Successful Pipeline Logging | Run a successful daily pipeline | Status JSON records PASS date and row count | PASS | Original Python run log records PASS; 50/50 files, 1,500 approved rows, 0 issues. | 2026-10-19_135823_319816_run.log; 2026-10-19_status.json
TC-014 | AC-014 | Failure Logging | Remove required store file and run pipeline | Status BLOCKED and missing filename recorded | PASS | Original Python failure log records MISSING_STORE_FILE (S004), BLOCKED, approved rows = 0. | TC-014_Failure_Logging.log (source: 2026-10-19_141718_952381_run.log)
TC-015 | AC-015 | Automatic Power BI Refresh | Review GitHub scheduled run, Neon SQL totals, Power BI refresh history and updated SQL Validation page. | Only approved data is loaded and refresh result recorded | PASS | 30-Oct snapshot: Neon and report both 7,500 approved rows (latest 29-Oct, 1,500); GitHub #7 Scheduled Success; Power BI Scheduled Completed and later On-demand Completed. New-batch unattended order not proved. | TC-015_01_GitHub_Scheduled_Success.png; TC-015_02_Neon_Approved_Sales_Snapshot.png; TC-015_03_PowerBI_Scheduled_Refresh_Completed.png; TC-015_04_PowerBI_SQL_Daily_Validation_7500.png

## UAT_Defect_Log
Defect_ID | Test_Reference | Issue_Description | Severity | Root_Cause | Corrective_Action | Status | Evidence
DEF-001 | TC-007 / Test Data Setup | Store 4 CSV contained changed Date format and scientific Sale_ID notation | Medium | Excel CSV automatic number/date conversion | Corrected CSV source values and reran validation | Resolved | Store 4 BLOCKED and recovery logs

## UAT_Summary
UAT_Metric | Value
Total_Test_Cases | 15
PASS | 15
FAIL | 0
BLOCKED | 0
Not_Run | 0
Formal_Stakeholder_Signoff | Pending external stakeholder approval (portfolio simulation)
Open_Requirement | Technical scope completed; same-new-batch fully unattended GitHub→Power BI sequencing not independently verified
Technical_Pass_Rate | 100%
Cloud_Snapshot_Date | 2026-10-30 ¦ 7,500 approved sales rows ¦ 9,852 units
TECHNICAL UAT: 15/15 case results recorded PASS for the simulated portfolio scope. TC-005–009 use isolated synthetic validation evidence; TC-011/012 interaction screenshots are user-confirmed. As of 30-Oct-2026, Neon and Power BI each show 7,500 approved rows. Scheduled GitHub Actions and scheduled Power BI refresh succeeded independently; a later on-demand refresh shows the new batch. Same-batch unattended run ordering and external stakeholder sign-off are not claimed.

## AS_IS_TO_BE_Gap_Analysis
Gap_ID | Process_Area | AS_IS_Manual_Process | TO_BE_Improved_Process | Identified_Gap | Expected_Business_Benefit | Implementation_Status | Related_Requirement
GAP-001 | Daily File Collection | Analyst manually collects daily store sales files | Store POS files are organized in date-wise input folders | Manual collection and tracking may cause delays | Standardized file intake and easier tracking | Implemented in Simulation | BR-001
GAP-002 | Missing File Detection | Analyst manually identifies stores that did not submit files | Python compares expected and received store files | Missing submissions may be difficult to identify quickly | Automatic detection of missing submissions | Implemented in Simulation | BR-002
GAP-003 | Data Combining | Analyst manually combines store CSV files in Excel | Power Query combines POS files from a folder | Manual combining requires repetitive work | Reduced repetitive combining work; Power Query refresh is currently manual | Implemented - Manual Refresh | BR-001
GAP-004 | Data Quality | Analyst manually checks invalid records | Power Query and Python validate transactions | Manual checking can miss data-quality problems | Consistent validation and exception identification | Implemented in Simulation | BR-003
GAP-005 | Report Approval | Analyst may prepare a report using incomplete data | Pipeline blocks approval when required checks fail | Incorrect or incomplete records may enter reporting | Prevention of invalid approved output | Implemented in Simulation | BR-004
GAP-006 | Approved Output | Analyst manually prepares clean reporting files | Python exports approved sales CSV after validation | Manual output preparation may be inconsistent | Standardized approved CSV generation | Implemented in Simulation | BR-005
GAP-007 | Execution Monitoring | Reporting errors are tracked manually | Python creates JSON status and execution logs | Limited automated evidence of failures | Better traceability and easier failure investigation | Implemented in Simulation | BR-009
GAP-008 | Daily Execution | Analyst starts processing manually | GitHub Actions runs the cloud Python validation + Neon loader on a schedule; Windows Task Scheduler was the legacy local approach | Manual execution depends on analyst availability | Laptop-independent scheduled execution; GitHub may delay jobs | Implemented — GitHub scheduled run #7 verified 30-Oct-2026 | BR-009
GAP-009 | Management Reporting | Analyst prepares static Excel MIS summaries | Power BI provides interactive sales and product dashboards | Static reports offer limited interactive analysis | Interactive KPI monitoring and filtering | Implemented for Historical Data | BR-006
GAP-010 | Automatic Dashboard Refresh | Updated reporting data requires separate refresh steps | Power BI Service refreshes its Neon PostgreSQL cloud source using a scheduled semantic-model refresh | Original gap (resolved in technical setup): dashboard refresh required separate manual steps | Approved rows are visible on online dashboards after a successful refresh; confirm schedule order for every new batch | Implemented - Scheduled Power BI refresh verified | BR-010

## KPI_Definition_Register
KPI_ID | KPI_Name | Business_Question | Calculation | Data_Source | Business_Decision | Target_Status
KPI-001 | Total Revenue | How much sales value did QuickKart generate? | SUM(Units * Product_Price) | Historical Sales + Products | Track business sales performance | Target Not Approved
KPI-002 | Total Gross Profit | How much gross profit did sales generate? | SUM(Units * (Product_Price - Product_Cost)) | Historical Sales + Products | Evaluate product profitability | Target Not Approved
KPI-003 | Gross Profit Margin % | How much gross profit is earned per 100 revenue? | Total Gross Profit / Total Revenue * 100 | Historical Sales + Products | Identify low-margin categories or stores | Target Not Approved
KPI-004 | Total Units Sold | How many product units were sold? | SUM(Units) | Historical Sales | Analyze customer demand and volume | Target Not Approved
KPI-005 | Total Transactions | How many sales transaction records exist? | COUNT(Sale_ID) | Historical Sales | Monitor transaction activity | Target Not Approved
KPI-006 | Average Selling Price | What was the average realized price per unit? | Total Revenue / Total Units Sold | Historical Sales + Products | Understand price mix and selling trends | Target Not Approved
KPI-007 | MoM Revenue Growth % | How did revenue change versus the previous month? | (Current Month Revenue - Previous Month Revenue) / Previous Month Revenue * 100 | Historical Sales + Calendar | Identify sales growth or decline | Target Not Approved
KPI-008 | Zero Stock Product Locations | How many store-product records have zero stock? | COUNT(Store-Product Pairs where Stock_On_Hand = 0) | Historical Inventory | Identify potential availability risks | Threshold Review Pending
KPI-009 | Approved Daily Transactions | How many approved daily sales records were loaded? | SQL: COUNT(*) FROM daily.approved_sales; BI: COUNTROWS('sql_Daily_Approved_Sales') (table name in this model) | Neon daily.approved_sales; Power BI SQL Daily Data Validation page | Verify daily reporting data availability | 7,500 approved transactions / 9,852 units as of 30-Oct-2026; point-in-time snapshot, updated with future batches

## RCA_5_Whys
Level | Business_Question | Analysis_or_Finding | Evidence_Status | Evidence_or_Validation | Next_Action
Problem | What happened in August 2023? | Revenue declined by $167471.79 (-20.22%) vs July | Verified | Monthly Revenue Variance SQL | Investigate revenue decline contributors
Why 1 | Why did overall revenue decrease? | Units fell from 63614 to 51193 (-19.53%); volume was the main mathematical driver | Verified | Monthly and Category SQL Analysis | Investigate which categories and products lost volume
Why 2 | Which categories contributed most? | Toys revenue fell $61223.47; Art & Crafts fell $51567.35; together 67.35% of overall decline | Verified | Category July-August Comparison | Drill down to product and store level
Why 3 | Why did customers buy fewer units in these categories? | Actual business cause is not yet established | Unverified | Requires product trends, promotions and demand data | Investigate product-level sales changes
Why 4 | Did stock availability or promotions affect sales? | Stockouts or promotional changes are possible hypotheses, not confirmed causes | Unverified | Requires historical stock and promotion records | Request relevant historical operational data
Why 5 | What underlying process issue caused the decline? | Root process cause cannot be confirmed with current evidence | Pending Further Investigation | Requires validated operational evidence and stakeholder review | Document root cause only after verification

## RCA_Findings_Action_Plan
Finding_ID | Business_Finding | Evidence | Business_Impact | Recommended_Action | Priority | Evidence_Status
RCA-001 | August 2023 revenue decreased by 20.22% | Monthly SQL Variance Analysis | Revenue decreased by 167471.79 USD | Investigate month-over-month changes by city category and product | High | Verified
RCA-002 | Units sold declined by 12421 | Monthly KPI Analysis | Lower sales volume contributed substantially to lower revenue | Investigate transaction and unit changes across stores and products | High | Verified
RCA-003 | Toys and Art & Crafts were major declining categories | Category SQL Drill-Down | Combined net revenue decline of 112790.82 USD | Prioritize detailed analysis of these two categories | High | Verified
RCA-004 | Lego Bricks showed the largest product revenue decline | Product SQL Analysis | Revenue decreased by 36870.78 USD and units decreased by 922 | Investigate Lego Bricks performance across stores | High | Verified
RCA-005 | Magic Sand showed a major sales-volume decline | Product SQL Analysis | Revenue decreased by 27390.87 USD and units decreased by 1713 | Analyze Magic Sand store-level sales changes | High | Verified
RCA-006 | Etch A Sketch revenue decreased by 55.04% | Product SQL Analysis | Revenue decreased by 17883.48 USD | Investigate product-level changes and historical availability | Medium | Verified
RCA-007 | Historical stock availability may have affected sales | Historical stock evidence is not available for the investigated months | Potential business cause cannot be confirmed | Request July and August 2023 inventory snapshots | High | Hypothesis - Unverified
RCA-008 | Promotion and demand changes may have affected sales | Promotion and customer-demand evidence not yet available | Underlying operational cause remains unconfirmed | Request historical promotion and demand data | Medium | Hypothesis - Unverified

## Statistical_Business_Findings
Finding_ID | Statistical_Measure | Evidence | Business_Interpretation | Recommended_Action | Evidence_Status
STAT-001 | Mean Sale Amount | 17.42 USD | Average historical transaction amount is 17.42 USD | Monitor average transaction value | Verified
STAT-002 | Median Sale Amount | 14.99 USD | Median is lower than mean; some high-value transactions may pull up the average | Use median alongside average for reporting | Verified
STAT-003 | Standard Deviation | 15.52 USD | Transaction values show substantial variability | Compare variability by category and city | Verified
STAT-004 | Interquartile Range | 11.00 USD | Middle 50 percent of transaction values span 11.00 USD | Use quartiles to understand typical sales distribution | Verified
STAT-005 | Upper Outlier Threshold | 36.49 USD | Transactions above 36.49 USD are high outliers under the 1.5 IQR rule | Investigate high-value transaction patterns | Verified
STAT-006 | High-Value Outlier Records | 89908 records; 10.84 percent | High-value records form a noticeable share of historical transactions | Review product and category contributions | Verified
STAT-007 | Low-Value Outlier Records | 0 records | No records are below the IQR lower limit of -7.51 USD | No lower outliers detected under this rule | Verified
STAT-008 | Top High-Value Product | Not calculated in the validated project evidence | Top product by high-value outlier count not established in saved evidence | Review product price and sales quantity patterns | Unverified - optional follow-up SQL
STAT-009 | Top City by Outlier Rate | Not calculated in the validated project evidence | City with highest outlier rate not established in saved evidence | Review city sales mix | Unverified - optional follow-up SQL
STAT-010 | Top Category by Outlier Rate | Not calculated in the validated project evidence | Category with highest outlier rate not established in saved evidence | Review category sales mix | Unverified - optional follow-up SQL

## 00_Portfolio_Overview
QUICKKART ¦ REQUIREMENTS & TEST EVIDENCE
Portfolio case study • simulated daily POS feeds • evidence snapshot 30 October 2026 • no external stakeholder sign-off
PROJECT FACT | EVIDENCE / QUALIFICATION
Project scope | 50-store daily simulated POS quality gate + historical retail analytics + cloud reporting
Historical sales | 829,262 transactions (historical analysis, not today's daily batch)
Approved daily sales | 7,500 approved daily transactions across five reporting dates (19, 22, 27, 28, 29 Oct 2026); snapshot 30-Oct-2026
Latest approved batch | Latest batch 29-Oct-2026: 1,500 transactions, 2,001 units
Approved units total | 9,852 units across 7,500 approved daily transactions (Neon + Power BI screenshot)
Power BI report | 5 Power BI report pages; SQL Daily Validation report displays 7,500 approved rows
Cloud workflow | GitHub Actions (simulated Python POS + validation) → Neon PostgreSQL → Power BI Service
Verification status | GitHub scheduled run #7 succeeded 30-Oct 11:13 AM; Power BI scheduled refresh 10:02 AM Completed; later 11:30 AM on-demand refresh Completed
Operational limit | Scheduled runs verified individually; automated GitHub-before-Power BI refresh for the same NEW batch not yet demonstrated
Formal approval | No real stakeholder sign-off; clarification, business-rule approval and formal production acceptance remain pending
Portfolio sharing | Use sanitized screenshots/README only; never share NEON_DATABASE_URL, passwords, connection strings or private backups
WORKSTREAM | STATUS | EVIDENCE | REMAINING NOTE
Requirements BRD/FRD | Documented | BR-001 through BR-010; FR-001 through FR-010 | Stakeholder confirmation pending
Agile stories / AC | Technical implementation | US-001..010; AC-001..015 | Formal business approval pending
Technical UAT | 15/15 technical cases recorded PASS | UAT_Test_Cases + UAT_Evidence_Manifest | TC-011/012 interaction images user-confirmed; external sign-off pending
Cloud database | Verified (30-Oct snapshot) | Neon daily.approved_sales 7,500 rows / 9,852 units | Snapshot; data may grow with new batches
Cloud job schedule | Scheduled run observed | GitHub Actions run #7 Scheduled Success, 30-Oct-2026 | Scheduled trigger timing is not guaranteed
Power BI schedule | Scheduled refresh observed | Power BI scheduled refresh Completed, 30-Oct 10:02 AM | 29-Oct new batch observed after later on-demand refresh
RCA / statistics | Mixed evidence | Verified findings and 3 explicitly unverified rankings | Do not present hypotheses as causal facts
RECRUITER EXPLANATION (COPYABLE)
I built a simulated 50-store retail analytics and quality-gate workflow using SQL, Python, Excel, Power Query, and Power BI. GitHub Actions validates daily POS batches, approved transactions land in Neon PostgreSQL, and Power BI Service reports the results. By 30 October 2026, I reconciled 7,500 approved transactions and 9,852 units across Neon and Power BI. Scheduled cloud jobs were demonstrated; full unattended same-batch sequencing and external stakeholder sign-off are not claimed.

## Cloud_Evidence_Register
Evidence_ID | Requirement/Test | Technical Evidence | Observed Result (30-Oct-2026 snapshot) | Evidence Location / Reference | Verification Limit
EV-001 | BR-001 to BR-005 / TC-001..009 | 50 simulated store CSV files validated in Python | PASS batch of 1,500 rows, or BLOCKED on invalid input | scripts/run_daily_quality_pipeline.py; saved UAT sample logs | Simulation; not live store feeds
EV-002 | BR-009 / TC-013..014 | JSON status, run log, exception CSV | Successful and blocked runs demonstrated | 04_Automation_Logs; GitHub run logs | GitHub uploaded QA artifacts have limited retention
EV-003 | BR-010 / TC-015 | GitHub Actions scheduled run #7 | Scheduled Success, 30-Oct-2026 11:13 AM IST (19 sec) | TC-015_01_GitHub_Scheduled_Success.png | Scheduled trigger may be delayed; independent workflow evidence
EV-004 | BR-010 / TC-015 | Power BI Service Refresh History | 30-Oct 10:02 AM Scheduled Completed; 11:30 AM On-demand Completed after GitHub run | TC-015_03_PowerBI_Scheduled_Refresh_Completed.png | New batch was observed after on-demand refresh; same-batch unattended ordering unproven
EV-005 | BR-005 / KPI-009 | Neon daily.approved_sales reconciliation | Five report dates: 7,500 sales rows; 9,852 units; latest 29-Oct: 1,500 rows / 2,001 units | TC-015_02_Neon_Approved_Sales_Snapshot.png | Point-in-time cloud snapshot; daily rows may increase
EV-006 | BR-006..008 / TC-010..012 | Power BI Service Cloud report | Five pages; SQL Daily Validation shows 7,500 rows; latest batch 29-Oct-2026 | TC-015_04_PowerBI_SQL_Daily_Validation_7500.png | View access depends on tenant/permissions
EV-007 | Formal stakeholder approval | No real external sign-off available | Pending | UAT_Summary B7; clarification logs | Do not label business approval 'Approved'
EV-008 | Fresh-batch unattended E2E | Fresh-batch end-to-end execution ordering | Not independently verified as fully unattended; 30-Oct scheduled PBI refresh preceded 11:13 AM GitHub batch, followed by on-demand refresh. | GitHub #7, Neon 7,500, Power BI 30-Oct refresh history and SQL Daily Validation screenshots | Do not claim the new batch reached Power BI via the earlier scheduled refresh
EV-009 | Statistical ranks STAT-008..010 | Verified SQL ranking output not uploaded | Unverified; not part of reported results | Statistical_Business_Findings rows 9..11 | No ranking values invented
EV-010 | TC-005..009 | Isolated synthetic Python validation cases | Units -3, unknown IDs, wrong date, approval block/recovery and 1,500-row approved CSV | TC-005..TC-009 isolated test files in 03_UAT_Testing_Evidence | Isolated tests are not cloud production run evidence

## UAT_Evidence_Manifest
QUICKKART ¦ UAT EVIDENCE REGISTER
15 technical UAT cases • final documentation snapshot: 30 October 2026 • evidence folder: 05_Business_Analysis_UAT / 03_UAT_Testing_Evidence
TEST CASE | EVIDENCE FILE(S) / FOLDER | FORMAT | SOURCE / TEST MODE | EVIDENCE RESULT | VERIFICATION NOTE
TC-001 | 2026-10-19_status.json | JSON | Original local Python run | 50/50 files, 1,500 approved; PASS | File content verified
TC-002 | TC-002_Date_Isolation.png | PNG | Original Power Query screenshot | 51 total; 50 selected-date; 1 other-date | Screenshot verified
TC-003 | TC-003_Missing_Store_BLOCKED.log | LOG | Original Python failure run | S004 missing; BLOCKED; 0 approved | Original log verified
TC-004 | TC-004_Duplicate_Sale_ID_BLOCKED.log | LOG | Original Python failure run | S003 line 3 duplicate ID; BLOCKED | Original log verified
TC-005 | TC-005_Invalid_Units_validation_exceptions.csv + test LOG / JSON | CSV + LOG + JSON | New isolated synthetic Python test | Units=-3; BLOCKED; no approved rows | Isolated, not production
TC-006 | TC-006_Unknown_Product_Store_ID_Evidence / 01_BLOCKED + 02_Recovery_PASS | LOG + CSV + JSON | New isolated synthetic Python test | Unknown IDs=9999; BLOCKED; correction PASS | Isolated, not production
TC-007 | TC-007_Wrong_Reporting_Date_Evidence / 01_BLOCKED + 02_Recovery_PASS | LOG + CSV + JSON | New isolated synthetic Python test | Wrong date blocked; correction PASS | Isolated, not production
TC-008 | TC-008_Report_Approval_Blocking_Evidence / 01_BLOCKED + 02_Recovery_PASS | LOG + JSON | TC-007 isolated test reused | Invalid batch 0 approved; recovery 1,500 | Reused test; not independent cloud gate
TC-009 | TC-009_Approved_Sales_2026-10-19_Isolated_Test.csv | CSV | New isolated synthetic PASS run | 1,500 valid approved transactions | Isolated CSV, not original cloud export
TC-010 | 01_Executive_Overview.png | PNG | Actual Power BI report screenshot | Historic KPIs visible; $14.44M sales | Visual display verified; SQL accuracy separate
TC-011 | TC-011_Sales_All_Filters_Before_REAL.png + TC-011_Store_Location_Downtown_After.png | PNG × 2 | Power BI interactive filter test | User reports slicer affected KPIs / visuals | AFTER image user-confirmed, not reviewed here
TC-012 | TC-012_Product_Analysis_REAL.png + TC-012_Product_Toys_Selected.png | PNG × 2 | Power BI category selection test | Product metrics and selection behavior reported | Selected image user-confirmed, not reviewed here
TC-013 | 2026-10-19_135823_319816_run.log + 2026-10-19_status.json | LOG + JSON | Original Python success run | PASS, 50 files, 1,500 rows, 0 issues | Original log / status verified
TC-014 | TC-014_Failure_Logging.log (from TC-003 original) | LOG | Original Python failure run | BLOCKED and missing S004 filename logged | Same log appropriately reused
TC-015 | TC-015_01_GitHub_Scheduled_Success.png; TC-015_02_Neon_Approved_Sales_Snapshot.png; TC-015_03_PowerBI_Scheduled_Refresh_Completed.png; TC-015_04_PowerBI_SQL_Daily_Validation_7500.png | PNG × 4 | GitHub + Neon + Power BI evidence | Scheduled jobs succeeded; 7,500 rows reconciled | Unattended same-batch sequence NOT established
TEST INTERPRETATION ¦ PASS means the documented technical test met its expected result within the stated environment. A deliberately BLOCKED invalid batch is a PASS for negative testing.
EVIDENCE LOCATION ¦ QuickKart_Recruiter_Portfolio / 05_Business_Analysis_UAT / 03_UAT_Testing_Evidence. Some files may be stored as extracted evidence subfolders.
CLOUD TIMELINE ¦ On 30-Oct: Power BI Scheduled 10:02 AM Completed; GitHub Scheduled #7 at 11:13 AM Success; Power BI On-demand 11:30 AM Completed; Neon and report showed 7,500 rows.
GOVERNANCE ¦ Simulated POS feed only. Formal real-world stakeholder approval not obtained. Do not imply contractual SLA or unattended same-batch ordering from available screenshots.